## WorkProducts
| ISO/IEC 29110 Work Products | ชื่อเอกสาร
1 | Project Initiation
WP.02 | Agreement
2 | Project Planning
Work Process Flow
Version Control Strategy
WP.10 | Project Plan (Val)
WP.22 | Validation Record | Ver
WP.07 | Meeting Record / เอกสารอื่นๆ ที่แสดงถึง PP ผ่านการตรวจสอบ (จากลูกค้า) | Val
WP.11 | Project Repository
3 | Software Implementation Initiation
WP.05 | Implementation Environment
4 | Software Requirements Analysis
WP.13 | Requirements Specification (Ver , Val)
WP.23 | Verification Record (SRS)
WP.22 | Validation Record (SRS)
5 | Software Design
WP.16 | Software Design (Ver)
WP.23 | Verification Record (SDD)
6 | Software Construction
WP.15 | Software Components
WP.14 | Software
7 | Project Execution, Assessment and Control
WP.04 | Correction Register
WP.07 | Meeting Record | Internal :
External :
WP.09 | Progress Status Record | Internal :
External :
WP.12 | Project Repository Backup
7 | Traceability Control
WP.21 | Traceability Record | RTM + Unit Test Result + Integrateion Test Result
8 | Software Testing
WP.19 | Test Cases and Test Procedures (Ver) | Unit test cases :
Integration test cases :
WP.23 | Verification Record (Integration test cases)
WP.20 | Test Report
Validation Record (UAT - Customer)
9 | Change Management
WP.03 | Change Request
11 | Software Product Assembly
WP.18 | Software User Documentation (Ver) | End User
WP.23 | Verification Record
WP.08 | Product Operation Guideline (Ver) | User Admin
WP.23 | Verification Record
WP.06 | Maintenance Documentation (Ver) | Techical
WP.23 | Verification Record
WP.17 | Software Product (Delivered)
12 | Project Closure
WP.01 | Acceptance Record